International School

Capstone Project 1

CMU SE - 450_C1SE.03

Project Plan Document

Version 1.0

Date: February 12th, 2025

FitAI – Smart Health & Fitness Assistant

Submitted by C1SE.56

Tri, Vo Van Duc 		 28211101270

Nhi, Nguyen Thi Dung	 28209054723

Toan, Pham Le Duc	 28211101330

Tu, Tran Van		 28214827896

Khanh, Truong Bao	 28211101470

Approved by

MSc. Tran Nhat Vinh

Review Panel Representative:

Name

Signature

Date

Capstone Project 1 – Mentor:

Name

Signature

Date

International School

Capstone Project 1

CMU SE - 450_C1SE.03

Project Plan Document

Version 1.0

Date: February 12th, 2025

FitAI – Smart Health & Fitness Assistant

Submitted by C1SE.56

Tri, Vo Van Duc 		 28211101270

Nhi, Nguyen Thi Dung	 28209054723

Toan, Pham Le Duc	 28211101330

Tu, Tran Van		 28214827896

Khanh, Truong Bao	 28211101470

Approved by

MSc. Tran Nhat Vinh

Review Panel Representative:

Name

Signature

Date

Capstone Project 1 – Mentor:

Name

Signature

Date

| DOCUMENT INFORMATION |  |  |  |
| --- | --- | --- | --- |
| Document Title | Project Plan Document |  |  |
| Author(s) | Tri, Vo Van Duc |  |  |
| Role | Forntend Dev, Backend Dev, Scrum Master |  |  |
| Date | 20 Seb 2025 | File name | C1SE56_ProjectPlan_SHFA_ver1.0.docx |
| URL |  |  |  |
| Access | Project and CMU Program |  |  |

REVISION HISTORY

| Version | Person(s) | Date | Description |
| --- | --- | --- | --- |
| 1.0 | All Members | 20 Seb 2025 | Create a Project Plan document |
| 1.1 | All Members | 01 May 2025 | Update Cost |

TABLE OF CONTENTS

- Introduction	1

1.1. Purpose	1

1.2. Project Overview	1

1.3. Project Deliverable	1

- Team Organization	2

2.1. Scrum Team Information	2

2.2. Role and Responsibility	2

2.3. Communication and Report	4

2.4. Communication Methodology	5

- Development Process	6

- Schedule and Cost	7

4.1. Detailed Schedule	7

4.2. Cost	11

4.2.1. Cost Person/Hours	11

4.2.2. Total Cost Estimate	11

- Project Risk	12

- Deliverables	14

LIST OF TABLE

Table 1: Scrum Team Organization	2

Table 2: Role and Responsibilities	2

Table 3: Communication Methodology	4

Table 4: Communication and Report	5

Table 5: Detailed Schedule	7

Table 6: Cost person/hours	11

Table 7: Total cost estimation	11

Table 8: Description Cost	11

Table 9: Rating for likelihood and seriousness of each risk	12

Table 10: Project Risk	12

Table 11: Deliverables	14

LIST OF FIGURE

Figure 1: Communication and Report	6

- Introduction

## 1.1. Purpose

This Project Plan provides a summary of the FitAI – Smart Health & Fitness Assistant project’s objectives, division of work, major milestones, required resources, overall schedule, and budget allocation. The plan is based on the approved project proposal and serves as a guideline for the project team to deliver the system on time, within scope, and according to the requirements.

## 1.2. Project Overview

FitAI is a web-based application designed to help users manage health and fitness effectively. The system provides:

- AI-driven personalized workout and nutrition recommendations based on user data (BMI, weight, goals).

- AI-powered food recognition from images with calorie estimation.

- Chatbot support for health-related queries and guidance.

- Smart reminders and notifications for diet and training schedules.

- Progress tracking and reporting with visual charts and badges.

The platform targets students, working adults, and families who need convenient and personalized solutions for health and fitness.

## 1.3. Project Deliverable

- Functional FitAI web application (with user and admin interfaces).

- AI Engine for workout/diet recommendations and calorie estimation.

- Notification service (reminders, alerts).

- Documentation: SRS, SDD, Test Plan, User Manual, Final Report.

- Prototype demo website.

# Team Organization

## Scrum Team Information

# Table 1. Scrum Team Organization

| Full Name | Email | Phone | Position |
| --- | --- | --- | --- |
| MSc.Tran Nhat Vinh | trannhatvinh88@gmail.com | 0918577644 | Mentor |
| Tri, Vo Van Duc | ninjaschool37@gmail.com | 0706007338 | Scrum Master and Dev-team |
| Nhi, Nguyen Thi Dung | dungnhi077@gmail.com | 0848091212 | Product Owner and Dev-team |
| Toan, Pham Le Duc | phamlductoan@gmail.com | 0365000847 | Dev-team |
| Tu, Tran Van | tranvantu9@dtu.edu.vn | 0935630298 | Dev-team |
| Khanh, Truong Bao | truongkhanh13572468@gmail.com | 0795781375 | Dev-team |

## Role and Responsibility

# Table 2. Role and Responsibilities

| Role | Responsibility | Name/Title |
| --- | --- | --- |
| Product Owner | Understand the user and customers with their needs. Collaborate with the development team. Manage the stakeholders and project vision. Describe the user experience and product features. Provides detailed user stories and prioritize the backlog. | Nhi, Nguyen Thi Dung |
| Scrum Master | Ensure the Scrum framework is followed. Facilitate Scrum ceremonies (daily, sprint planning, review, retrospective). Remove impediments that block the team’s progress. Maintain team focus and encourage productivity. Coach members on Agile principles and practices. Ensure commitments are met according to the plan. | Tri, Vo Van Duc |
| Secretary | Record the content of group meetings and activities of the member. | Tri, Vo Van Duc |
| Reviewer | Review documents. | All Members |
| Developer | Analysis of the functions and requirements of the product. Develop user interface (ReactJS) and backend logic (Node.js). Design and maintain the database (MySQL). Integrate AI modules (recommendation engine, chatbot). Conduct coding, unit testing, and debugging. | All Members |
| Analyzer | Collect and refine user requirements. Analyze requirements and create clear specifications. | All Members |
| Tester | Do the Test plan. Creation of test designs, test processes, test cases, and test data. Execute functional and integration testing. Report defects and verify fixes meet acceptance criteria. | All Members |
| Mentor | Provide academic and technical guidance. Monitor project progress and quality. Review deliverables and ensure alignment with Capstone requirements. Support the team in resolving difficulties. | Vinh, Tran Nhat |

## Communication and Report

# Table 3. Communication Methodology

| Audience/ Attendees | Topic/ Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Mentor and Team member | Project Progress Review | Weekly | Meeting, Trello, Zalo |
| Team Member | Project Progress Review and Daily Meeting | Daily | Trello, GitHub, Zoom, Zalo |

## Communication Methodology

# Table 4. Communication and Report

| Type of communication | Methods, tools | Frequency | Information | People |
| --- | --- | --- | --- | --- |
| Communication among group |  |  |  |  |
| Scrum meeting | Face-to-face or Hangouts | Every two day | Informed about what was done in the last 24 hours, working on plans for today, the difficulties encountered and the solutions required, just meeting 10-15 minutes. | Project team |
| Sprint Planning Meeting | Meet face to face | 15-20 days | All members of the team together to analyze the requirements and functions, work on the sprint going to do, planning and design for the sprint. | Project team |
| Retrospective meeting | Meet face to face | 15-20 days | Complete documentation. For each stage, sharing materials, given the strengths and weaknesses of each. Period for each member and the solution calculated measurement project. | Project team and Mentor |
| Demo | Meet face to face or meeting online | Every day | A web-based task tracking system. To manage or divide tasks, and report bugs/issues. | Project team. |

# Development Process

Figure 1: Communication and Report

The development process for the FitAI – Smart Health & Fitness Assistant project follows the Scrum framework, which is an iterative and incremental agile methodology for managing software development. The benefit of the methodology:

- Scrum is designed to handle complex projects where it is difficult to plan everything in advance.

- It applies mechanisms of empirical process control, meaning progress is guided by frequent feedback loops and adaptation, instead of relying on rigid command-and-control structures.

- Scrum emphasizes collaboration, continuous improvement, and empowering the team to make decisions at the operational level to respond effectively to uncertainties.

Benefits of the Scrum methodology:

- The project can respond easily to change.

- Problems are identified early.

- Customers get the most valuable features delivered first.

- Work done will better meet the customer’s needs.

- Improved team productivity.

- Ability to maintain a predictable delivery schedule.

# Schedule and Cost

## Detailed Schedule

# Table 5. Detailed Schedule

| No. | Task Name | Start | Finish | Effort |
| --- | --- | --- | --- | --- |
| 1 | Initial | 19/08 | 26/08 | 40 hrs |
| 1.1 | Gathering Requirement | 19/08 | 21/08 | 12 hrs |
| 1.1.1 | Get requirements from Mentor & Stakeholders | 19/08 | 19/08 | 4 hrs |
| 1.1.2 | Analyze requirements and clarify scope | 20/08 | 21/08 | 8 hrs |
| 1.2 | Create Proposal Document | 22/08 | 26/08 | 28 hrs |
| 1.2.1 | Write Problem Statement & Objectives | 22/08 | 22/08 | 6 hrs |
| 1.2.2 | Draft Survey / Existing Solutions | 23/08 | 23/08 | 6 hrs |
| 1.2.3 | Define Scope & Key Features | 24/08 | 24/08 | 6 hrs |
| 1.2.4 | Review & finalize proposal with mentor | 25/08 | 26/08 | 10 hrs |
| 2 | Start Up | 27/08 | 05/09 | 50 hrs |
| 2.1 | Project Kick-off Meeting | 27/08 | 28/08 | 4 hrs |
| 2.2 | Initiation Documents | 29/08 | 05/09 | 46 hrs |
| 2.2.1 | Create Product Backlog | 29/08 | 30/08 | 10 hrs |
| 2.2.2 | Draft Project Charter | 31/08 | 31/08 | 6 hrs |
| 2.2.3 | Create Project Plan (v1) | 01/09 | 02/09 | 12 hrs |
| 2.2.4 | Architecture Design Document | 03/09 | 04/09 | 10 hrs |
| 2.2.5 | Review & approval with mentor | 05/09 | 05/09 | 8 hrs |
| 3 | Development | 06/09 | 02/12 | 600 hrs |
| 3.1 | Sprint 1 – Registration & Profile | 06/09 | 20/09 | 100 hrs |
| 3.1.1 | Design DB schema for User & Profile | 06/09 | 08/09 | 15 hrs |
| 3.1.2 | Implement Registration Form (Frontend + Backend) | 09/09 | 11/09 | 20 hrs |
| 3.1.3 | Implement Login + Authentication (JWT, Bcrypt) | 12/09 | 13/09 | 15 hrs |
| 3.1.4 | Forgot/Reset Password with Email | 14/09 | 15/09 | 15 hrs |
| 3.1.5 | Health Profile Input (Height, Weight, Goals) | 16/09 | 18/09 | 20 hrs |
| 3.1.6 | Unit Test & Debug Authentication/Profile | 19/09 | 20/09 | 15 hrs |
| 3.2 | Sprint 2 – Workout Recommendation | 21/09 | 05/10 | 100 hrs |
| 3.2.1 | Collect workout dataset & define exercise rules | 21/09 | 22/09 | 15 hrs |
| 3.2.2 | Build AI recommendation model (baseline) | 23/09 | 26/09 | 25 hrs |
| 3.2.3 | Develop Workout Recommendation API | 27/09 | 29/09 | 20 hrs |
| 3.2.4 | Frontend UI for Workout Suggestion | 30/09 | 01/10 | 20 hrs |
| 3.2.5 | Integration + Testing module | 02/10 | 05/10 | 20 hrs |
| 3.3 | Sprint 3 – Nutrition & Calorie Estimation | 06/10 | 20/10 | 100 hrs |
| 3.3.1 | Design Nutrition Database schema | 06/10 | 07/10 | 15 hrs |
| 3.3.2 | Food Logging UI (manual input) | 08/10 | 09/10 | 20 hrs |
| 3.3.3 | Integrate AI Food Recognition (image input) | 10/10 | 12/10 | 25 hrs |
| 3.3.4 | Calorie Calculation & Estimation logic | 13/10 | 15/10 | 20 hrs |
| 3.3.5 | Testing Nutrition Module | 16/10 | 20/10 | 20 hrs |
| 3.4 | Sprint 4 – Chatbot & Reminder | 21/10 | 04/11 | 100 hrs |
| 3.4.1 | Integrate Chatbot (health Q&A) | 21/10 | 24/10 | 30 hrs |
| 3.4.2 | Daily Reminder Service (Email/SMS) | 25/10 | 27/10 | 25 hrs |
| 3.4.3 | Notification UI (user settings) | 28/10 | 29/10 | 20 hrs |
| 3.4.4 | Test accuracy + user interactions | 30/10 | 04/11 | 25 hrs |
| 3.5 | Sprint 5 – Progress Tracking & Admin Dashboard | 05/11 | 18/11 | 100 hrs |
| 3.5.1 | Progress Tracking UI with Charts | 05/11 | 07/11 | 20 hrs |
| 3.5.2 | Badges & Achievement Rewards | 08/11 | 09/11 | 20 hrs |
| 3.5.3 | Admin Dashboard (account & data management) | 10/11 | 13/11 | 30 hrs |
| 3.5.4 | Export Reports & Analytics | 14/11 | 15/11 | 15 hrs |
| 3.5.5 | Testing & Debugging Admin/Tracking | 16/11 | 18/11 | 15 hrs |
| 3.6 | Sprint 6 – System Integration & Testing | 19/11 | 02/12 | 100 hrs |
| 3.6.1 | Integration Test (Frontend + Backend + DB) | 19/11 | 21/11 | 25 hrs |
| 3.6.2 | AI Engine full integration test | 22/11 | 23/11 | 20 hrs |
| 3.6.3 | Performance & Load Testing | 24/11 | 26/11 | 20 hrs |
| 3.6.4 | Security Testing (encryption, SQL injection) | 27/11 | 28/11 | 15 hrs |
| 3.6.5 | Bug fixing & optimization | 29/11 | 02/12 | 20 hrs |
| 4 | Project Retrospective | 03/12 | 05/12 | 12 hrs |
| 4.1 | Conduct Retrospective meeting | 03/12 | 03/12 | 4 hrs |
| 4.2 | Document lessons learned | 04/12 | 04/12 | 4 hrs |
| 4.3 | Final Review with mentor | 05/12 | 05/12 | 4 hrs |
| 5 | Final Release | 11/12 | 12/12 | 8 hrs |
| 5.1 | Submit Final Report + Demo | 11/12 | 11/12 | 4 hrs |
| 5.2 | Final Presentation & Delivery | 12/12 | 12/12 | 4 hrs |

## Cost

### Cost Person/Hours

# Table 6. Cost person/hours

| Full Name | Role | Salary Rate (USD/hour) |
| --- | --- | --- |
| Tri, Vo Van Duc | Scrum Master | $2 |
| Nhi, Nguyen Thi Dung | Product Owner | $2 |
| Toan, Pham Le Duc | Team Member | $2 |
| Tu, Tran Van | Team Member | $2 |
| Khanh, Truong Bao | Team Member | $2 |

### Total Cost Estimate

Table 7. Total cost estimation

| No. | Criteria | Price | Total (USD) |
| --- | --- | --- | --- |
| 1 | Working cost | $2/hours | $3000 |
| 2 | Deployment cost | $20/month | $50 |
| 3 | Contingency cost | $300 | $305 |
|  | Total cost |  | $3355 |

Table 8. Description Cost

| Description | Amount | Unit |
| --- | --- | --- |
| Number of Members | 5 | Person |
| Number of working hours per day | 4 | Hours |
| The cost of working per hour per member | 2 | USD |
| The duration of the project | 2.5 | Months |
| The number of working days | 75 | Days |

The explanation for the table:

- Amount of working cost = 5 members * 4 hours/day * $2/hour * 75 days = $3000

- Deployment cost = $20 * 2.5 months = $50

- Contingency cost = 10% * (amount of working cost + deployment cost) = $305

# Project Risk

# Table 9. Rating for likelihood and seriousness of each risk

| RATING FOR LIKELIHOOD AND SERIOUSNESS OF EACH RISK |  |  |  |
| --- | --- | --- | --- |
| L | Rated as Low | E | Rated as Extreme (Used for Seriousness only) |
| M | Rated as Medium | NA | Not Assessed |
| H | Rated as High |  |  |

Table 10. Project Risk

| Risk | Definition | Level (Seriousness) | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| AI inaccuracy | AI may give wrong workout or meal suggestions | H | M | Retrain model with diverse datasets, validate output with benchmarks. |
| Module integration issues | Integration between frontend, backend, database, and AI engine may fail | M | M | Use standard APIs, perform frequent integration testing. |
| Security vulnerabilities | Risk of user data leakage, breaches during transmission/storage | H | M | Apply HTTPS, encrypt sensitive data, backup regularly. |
| Schedule delays | AI model training or testing may take longer than expected | H | M | Break down into smaller milestones, add buffer time |
| Cross-platform challenges | Web app may fail on some browsers or devices | M | M | Test on Chrome, Edge, Firefox, and mobile browsers. |
| Testing bottleneck | If testing is left until the end, bugs may pile up | M | H | Apply CI/CD, continuous testing during each sprint. |
| Resource gap | Team lacks deep AI expertise and privacy law knowledge | M | H | Consult mentor/experts, do online training, research references. |
| Team turnover | A member may get busy with exams or drop out | M | M | Crosstrain all members, use GitHub & documentation for handover. |
| Team workload | Academic responsibilities reduce project time | M | H | Prioritize core features, allocate weekend/extra sessions. |

# Deliverables

Table 11. Deliverables

| No. | Document | Deadline | File Name |
| --- | --- | --- | --- |
| 1 | Proposal Document | 25 Aug 2025 | C1SE056_Proposal_SHFA_ver2.0.docx |
| 2 | Product Backlog Document | 27 May 2025 | C1SE03_ProductBacklog_PRH_ver1.1.docx |